## Error and Requirment
SL No. | Module | Feature | Problems / Questions | Note from RK Software | Portal Type | Date and TIme | Date and Time | Note | meemmahmuda70@gmail.com | meemmahmuda70@gmail.com | Reply From Dev Team | Note
1 | Manage Institutes | Create Institute | The institute cannot be created. |  | Back Office(RKAdmin) |  | 2026-01-24 13:17 | 2. Still same problem 3. Solved | 2026-01-24 13:22 |  | Completed
2 | Institutes | Institute Create | During institute creation, the user password that is set cannot be viewed later. If it is forgotten, there is no way to see it again. |  | Back Office(RKAdmin) |  | 2026-01-24 13:21 |  |  |  | Open
3 | Institutes | Institute List | The school logo is not showing on the system after upload. |  | Back Office(RKAdmin), Institute Portal(RKEIMS) |  |  | 2. Solved | 2026-01-24 13:22 |  | Completed
4 | Roles & Permission | Create Role | From the Create Role menu, the role cannot be created. |  | Back Office(RKAdmin) |  | 2026-01-24 13:23 |  |  |  | Completed
5 | Roles & Permission | Create Admin | From the Create Admin menu, which admin is actually being created? During institute creation, we already create a user. So which one is this? |  | Back Office(RKAdmin)
6 | Institutes | Institute List | When I try to update the institute, the Billing Type shows Profile Count, but I did not select this. I selected Fixed Yearly. |  | Back Office(RKAdmin) |  |  |  | 2026-01-24 13:22 |  | Completed
7 | Institutes | Institute List | When I try to update, the Profile count , Max No. of Students field shows empty, even though I had entered a value before. |  | Back Office(RKAdmin) | [5 empty] | Completed
8 | Institutes | Admission | In the Admission menu, under the Instruction submenu, the Add Instruction button is not working. |  | Back Office(RKAdmin) | [5 empty] | Pending
9 | Master Setting | Administration | Is the admin created from the Admin List menu under Administration the same as the one created from the Create Admin menu? |  | Back Office(RKAdmin)
10 | Master Setting | General Configs | What is the function of the General Configs menu, and what should be done there? |  | Back Office(RKAdmin) |  |  | We discussed the general configuration in the institute portal, but my question is about the back office general portal. | 2026-01-24 13:22 |  | Completed
11 | Report | Institute Report | Are Institute Report and Institute List the same? Both are going to the same URL. |  | Back Office(RKAdmin) |  |  |  | 2026-01-24 13:22 | 2026-01-24 13:17 | Completed
12 | Student Info | Registration | Not Save |  | Institute Portal(RKEIMS) |  |  |  | 2026-01-24 13:17 |  | Completed
13 | Student Info | Registration |  |  | Institute Portal(RKEIMS) |  |  |  | 2026-01-24 13:22 | 2026-01-24 13:17 | Completed
14 | Student Info | Registration | Student is not enrolling. |  | Institute Portal(RKEIMS) |  |  |  | 2026-01-24 13:17 |  | Completed
15 | Student Info | Registration | Excel Form page button is not working. | The Excel form page button is working, but when I enroll students using the Excel file upload, those students are not showing in the student list. | Institute Portal(RKEIMS) |  |  |  | meemmahmuda70@gmail.com | meemmahmuda70@gmail.com | Completed
16 | Student Info | Update | In Student Info → Update → Basic Info the information is not updating. Also the Excel file button is not working. |  | Institute Portal(RKEIMS) |  |  |  | 2026-01-24 15:37 |  | Completed
17 | Student Info | Update | Academic info cannot be updated. | In Academic Info-- updating Group, Section, and Category is not working. | Institute Portal(RKEIMS) |  |  |  | meemmahmuda70@gmail.com |  | Completed
18 | Student Info | Update | Other info cannot be updated. | In Other Info, the Export button is not working | Institute Portal(RKEIMS) |  |  |  | meemmahmuda70@gmail.com |  | Completed
19 | Student Info | Promotion | Students without merit cannot be migrated. |  | Institute Portal(RKEIMS) | [5 empty] | Completed
20 | Student Info | Promotion | Promotion push-back is not working it still appears in the list. |  | Institute Portal(RKEIMS) | [5 empty] | Completed
21 | Student Info | Summery | Report → Summary - Total Student is not showing. |  | Institute Portal(RKEIMS) |  |  |  | 2026-01-24 13:17 |  | Completed
22 | Student Attendance | Update | Student Attendance → Update menu is not working. |  | Institute Portal(RKEIMS)
23 | Student Attendance | Leave Manage | Leave Manage → Leave Reason this page is not showing |  | Institute Portal(RKEIMS) | [5 empty] | Pending
24 | Student Attendance | Leave Manage | In Leave Input the wrong page is showing. |  | Institute Portal(RKEIMS) | [5 empty] | Pending
25 | Student Attendance | Leave Manage | Leave Application ID search is not working. |  | Institute Portal(RKEIMS) | [5 empty] | Pending
26 | Student Attendance | Device Data | Device Data → Data Uploaded , Data Process menus- the Student Report page is showing instead of the correct page. |  | Institute Portal(RKEIMS) | [5 empty] | Pending
27 | Student Attendance | Report | Report → Summary, Details Info, and Device Report- the wrong page is showing. |  | Institute Portal(RKEIMS) | [5 empty] | Completed
28 | Exam Management | Setting | Class Test → Assign the exam delete option is not working. |  | Institute Portal(RKEIMS) | [5 empty] | Completed
29 | Exam Management | Setting | Semester Exam → Exam Setting → Exam Startup→ Class Test Mapping - no data can be entered here |  | Institute Portal(RKEIMS) |  |  |  | 2026-01-24 13:17 |  | Completed
30 | Exam Management | Semester Exam | Semester Exam → Mark Input is not working. |  | Institute Portal(RKEIMS) | [5 empty] | Completed
31 | Master Settings | Basic Setup | In Basic Setup District ,Thana data is not saving. |  | Institute Portal(RKEIMS) | [5 empty] | Completed
32 | Master Settings | General Configuration | General Configuration menu- values are not showing. |  | Institute Portal(RKEIMS) |  |  |  | 2026-01-24 16:34 |  | Completed
33 | Student Info | Update | Student Info → Basic Info, the Student Type and Residential Type are shown but in Other Info they do not match. |  | Institute Portal(RKEIMS) |  |  |  | 2026-01-24 17:12 |  | Completed
34 | Student Management | Student Attendance | From Student Attendance → ID Mapping, when I click Push Data, it shows a success message, but I haven’t connected any device. So where did the data go? |  | Institute Portal(RKEIMS)
35 | Student Management | Take Attendance | I tried to change the section-wise , Exam Attendance update from Present to Absent, but no changes happened. |  | Institute Portal(RKEIMS) | [5 empty] | Completed
36 | HR Management | HR Management | The HR Management module is not working correctly, some pages are not showing. |  | Institute Portal(RKEIMS)
37 | Student Management | Student Attendance | changing Attendance ID auto-changes Student ID, which is not correct. |  | Institute Portal(RKEIMS) | [5 empty] | Completed
38 | Master Setting | Class Setup | In Master Settings, what is the Class Setup Mapping system? How should sections and groups be selected—all at once or one by one? |  | Institute Portal(RKEIMS) | [5 empty] | Check Note
39 | Master Setting | Subject Setup | once a subject is applied, it can’t be changed later |  | Institute Portal(RKEIMS) | [5 empty] | Completed
40 | Master Setting | Subject Setup | same serial number can be used for multiple subjects. Why? |  | Institute Portal(RKEIMS) | [5 empty] | Completed
41 | Fees Management | Fee Mapping | In Fees Management → Fee Mapping, mapped fees cannot be deleted |  | Institute Portal(RKEIMS) | [5 empty] | Completed
42 | Fees Management | Amount Setup | Student-wise amount setup is not working properly |  | Institute Portal(RKEIMS) | [5 empty] | Completed
43 | Exam Management | Semester Exam | Exam Setting - Exam onfig -the values are not showing in the merit process type dropdown |  | Institute Portal(RKEIMS) |  | 2026-01-25 12:30 |  |  |  | Completed
44 | Master Setting | Statrtup | Master Settings → Startup here I need to edit the serial number again and again |  | Institute Portal(RKEIMS) | 2026-01-26 11:13 |  |  |  |  | Completed
45 | Master Setting | Class Setup | In Class Map, some changes have appeared. I can’t understand how the mapping works here. |  | Institute Portal(RKEIMS) | 2026-01-26 15:44 |  |  |  |  | Completed
46 | Master Setting | Subject Configure | In Subject Configure, what is the function of the Copy To button? Also when adding a subject an icon appears on the right side. If I click it the subject gets deleted. Is this icon’s function correct? |  | Institute Portal(RKEIMS) | 2026-01-26 15:47 |  |  |  |  | Completed
47 | Master Setting | 4th subject | In the 4th subject assigning section, I assigned a subject to a student. But after refreshing, the student still shows here. Since the subject is already assigned, the student should not appear. |  | Institute Portal(RKEIMS) | 2026-01-26 15:51 |  |  |  |  | Check Note
48 | Master Setting | Irregular-Subject | Same issue like 47 no |  | Institute Portal(RKEIMS) | 2026-01-26 15:58 |  |  |  |  | Check Note
49 | Student Management | Basic Info | In Basic Info, the date of birth is not stored in Excel and also does not show. |  | Institute Portal(RKEIMS) | 2026-01-26 15:59 |  |  |  |  | Completed
50 | Student Management | Basic Info | In Basic Info, if I try to upload Excel after editing it, the file does not upload and shows an error. |  | Institute Portal(RKEIMS) | 2026-01-26 16:01 |  |  |  |  | Completed
51 | Student Management | Academic Info | In Academic Info → Update All, I changed a student to another class, but there is no way to move them back to the previous class. | this section fix and explain after I note here. | Institute Portal(RKEIMS) | 2026-01-26 16:04 |  |  | meemmahmuda70@gmail.com |  | Completed
52 | Student Management | Academic Info | From Update Group, I changed a student’s group from BS to Science. Now the group column shows blank, and if I search in the student list, the student still appears in BS instead of Science. | this section fix and explain after I note here. | Institute Portal(RKEIMS) | 2026-01-26 16:07 |  |  | meemmahmuda70@gmail.com |  | Completed
53 | Student Management | Academic Info | The Update Section feature is not working. | this section fix and explain after I note here. | Institute Portal(RKEIMS) | 2026-01-26 16:08 |  |  | meemmahmuda70@gmail.com |  | Completed
54 | Student Management | Academic Info | The Update Category feature is not working. | this section fix and explain after I note here. | Institute Portal(RKEIMS) | 2026-01-26 16:09 |  |  | meemmahmuda70@gmail.com |  | Completed
55 | Student Management | Academic Info | In Academic Info, the Guardian Contact column does not show any value. |  | Institute Portal(RKEIMS) | 2026-01-26 16:10 |  |  |  | meemmahmuda70@gmail.com | Completed
56 | Student Management | Other Info | In Other Info, the Marital Status drop-down does not appear. |  | Institute Portal(RKEIMS) | 2026-01-26 16:13 |  |  |  | meemmahmuda70@gmail.com | Completed
57 | Student Management | Other Info | In Student Type, it shows Non-Regular, but it should be Irregular. |  | Institute Portal(RKEIMS) | 2026-01-26 16:13 |  |  |  | meemmahmuda70@gmail.com | Completed
58 | Student Management | Other Info | The following fields are not being stored, and they do not appear in Excel or PDF: present division, present district, mother income, father address, mother address, permanent division, guardian relation, father email, father NID, date of birth, father income, father education, father profession, mother email, mother NID, mother profession, permanent district. Even after editing the Excel file and uploading it again, the values still do not show. |  | Institute Portal(RKEIMS) | 2026-01-26 16:18 |  |  |  | meemmahmuda70@gmail.com | Completed
59 | Student Management | Promotion | In Promotion Push Back, the name, group, and contact values do not show. |  | Institute Portal(RKEIMS) | 2026-01-26 16:20 |  |  |  |  | Completed
60 | Student Management | Summery | In the Religion report, there are Hindu students, but they do not show in the report. If I update the religion, it does not get stored and still shows the previous value. |  | Institute Portal(RKEIMS) | 2026-01-26 16:21 |  |  |  | meemmahmuda70@gmail.com | Completed
61 | Student Management | Summery | The following fields do not store values in the student list: date of birth, guardian relation, nationality, NID, height, weight, special disease, marital status, student email, father NID, father email, father address, father profession, father income, father education, mother NID, mother email, mother address, mother profession, mother income, mother education, present division, present district, permanent division, permanent district, education info, quota name, vaccinated status, and vaccine name. |  | Institute Portal(RKEIMS) | 2026-01-26 16:30 |  |  |  |  | Completed
62 | Student Management | Summery | In Other Info, the quota name, vaccinated status, and vaccine name input fields are missing. |  | Institute Portal(RKEIMS) | 2026-01-26 16:31 |  |  |  |  | Completed
63 | Student Attendance | Take Attendance | In Take Attendance → Section Wise, if I change attendance from Present to Absent, it still shows as Present. But, in Update Attendance, it shows as Absent. |  | Institute Portal(RKEIMS) | 2026-01-26 16:34 |  | In the Attendance section, the status is set to default initially. To check or update the present status, please use the ‘Section Attendance Update’ tab |  |  | Completed
64 | Student Attendance | Take Attendance | From Exam Attendance, I changed the attendance to Absent, but in Update Attendance, the absent status does not show and cannot be edited. |  | Institute Portal(RKEIMS) | 2026-01-26 16:35 |  |  |  |  | Completed
65 | Student Attendance | Leave Manage | In Leave Management, the Leave Reason page does not show. |  | Institute Portal(RKEIMS) | 2026-01-26 16:37 |  |  |  | meemmahmuda70@gmail.com
66 | Student Attendance | Leave Manage | In Leave Reason, the wrong page is displayed. |  | Institute Portal(RKEIMS) | 2026-01-26 16:38 |  |  |  | meemmahmuda70@gmail.com
67 | Student Attendance | Leave Manage | In Leave Application, if I search by Student ID, no data is displayed. |  | Institute Portal(RKEIMS) | 2026-01-26 16:40 |  |  |  | meemmahmuda70@gmail.com
68 | Student Attendance | Device data | In the Device Data menu, the wrong page is displayed in all sub-menus. |  | Institute Portal(RKEIMS) | 2026-01-26 16:40 |  |  |  | meemmahmuda70@gmail.com
69 | Student Attendance | Report | In Report → Summary, no sub-menu shows the correct page. |  | Institute Portal(RKEIMS) | 2026-01-26 16:42 |  |  |  |  | Completed
70 | Student Attendance | Report | In the Attendance Sheet, no attendance data is shown only student details are displayed. |  | Institute Portal(RKEIMS) | 2026-01-26 16:43 |  |  |  |  | Completed
71 | Fees Management | Amount Setup | In Amount Setup, the class-wise amount cannot be set up an error occurs. |  | Institute Portal(RKEIMS) | 2026-01-26 16:54 |  |  |  |  | Completed
72 | Fees Management | Amount Setup | In Student-wise Amount, the Excel file does not download, the fee,fine amount cannot be changed, and the values are not stored. |  | Institute Portal(RKEIMS) | 2026-01-26 16:55 |  |  |  |  | Check Note
73 | Fees Management | Fee Remove | In Fee Remove → Fee Head, the feature does not work. |  | Institute Portal(RKEIMS) | 2026-01-26 17:00 |  |  |  | meemmahmuda70@gmail.com | Completed
74 | Fees Management | Fee Remove | In Fee Remove → Fee Sub Head, the feature does not work. |  | Institute Portal(RKEIMS) | 2026-01-26 17:02 |  |  |  | meemmahmuda70@gmail.com | Completed
75 | Fees Management | Fee Collection | In Quick Collection, the Collection Invoice does not work. |  | Institute Portal(RKEIMS) | 2026-01-26 17:05 |  |  | meemmahmuda70@gmail.com |  | Completed
76 | Fees Management | Report | In Waiver Info, the Waiver Details do not show. |  | Institute Portal(RKEIMS) | 2026-01-26 17:07 |  |  |  |  | Completed
77 | Fees Management | Online Payment | In the online payment details section, manual collection details are appearing |  | Institute Portal(RKEIMS) | [5 empty] | Completed
78 | Exam Management | Class Test | No report is shown in the class test section |  | Institute Portal(RKEIMS) |  |  |  |  | meemmahmuda70@gmail.com
79 | Exam Management | Mark Entry | In class test mark entry, if more marks are entered than the total marks, it will turn red. |  | Institute Portal(RKEIMS) | [5 empty] | Check Note
80 | Exam Management | Mark Input | I configured a new subject but when I go to mark input it throws an error. |  | Institute Portal(RKEIMS) | [5 empty] | Completed
81 | Message & Notification | Phone Book | Add Selected to Phone Book button is showing an error and not adding the contact. |  | Institute Portal(RKEIMS) | [5 empty] | Completed
82 | Administration | Create User | From Allow Backdated to Dashboard View no dropdowns are visible. |  | Institute Portal(RKEIMS) | [5 empty] | Completed
84 | Routine Management | Routine | All menus page missing |  | Institute Portal(RKEIMS) | [5 empty] | Completed
Still cannot create institution.
Institute logo not showing in Institute List.
I have added students, but the Student List button does not show the student list.

## Update Menu 23 Jan 26
Label | Menu | Sub Menu | Feature | Sub Feature | Modul wise Complete (%) | Complete (%)
69.19%
No Label for Home
Home
Dashboard
Dashboard
Student Management
| Student Info |  |  |  | 100%
Registration
Enrollment Form
|  |  |  | Custom ID |  | 100%
Excel Form
|  |  |  | Custom ID |  | 100%
Update
|  |  | Basic Info |  |  | 100%
|  |  | Academic Info |  |  | 100%
|  |  | Others Info |  |  | 100%
|  |  | Status |  |  | 100%
Promotion
|  |  | With Merit |  |  | 100%
|  |  | Without Merit |  |  | 100%
|  |  | Promotion Pushback |  |  | 100%
Report
Summery
|  |  |  | Total Student |  | 100%
|  |  |  | Gender Info |  | 100%
|  |  |  | Religion Info |  | 100%
Details
|  |  |  | Student List |  | 100%
| Student Attendance |  |  |  | 63.81%
Setting
Attendance Time Setup
|  |  |  | Day Wise |  | 100%
|  |  |  | Period Wise |  | 100%
|  |  | ID Mapping |  |  | 100%
Take Attendance
|  |  | Section Wise |  |  | 100%
|  |  | Exam Attendance |  |  | 100%
Leave Manage
|  |  | Leave Reason |  |  | 0%
|  |  | Leave Input |  |  | 0%
|  |  | Leave Application |  |  | 0%
Delete
|  |  | Section Attendance |  |  | 0%
|  |  | Exam Attendance |  |  | 0%
|  |  | Leave |  |  | 0%
Report
Blank Sheet
|  |  |  | Section Wise |  | 100%
Summery
|  |  |  | Shift Wise |  | 80%
|  |  |  | Class Wise |  | 80%
|  |  |  | Section Wise |  | 80%
Details Info
|  |  |  | Attendance Sheet |  | 80%
|  |  |  | Attendance Status |  | 80%
|  |  |  | Attendance Info |  | 80%
|  |  |  | Exam Attendance |  | 80%
Device Report
|  |  |  | Mapping Device |  | 100%
|  |  |  | Device Data Log |  | 80%
HR Management
| Human Resource |  |  |  | 95.33%
Settings
|  |  | Department |  |  | 100%
|  |  | Designation |  |  | 100%
|  |  | Duty Shift |  |  | 100%
|  |  | Job Type |  |  | 100%
Registration
|  |  | Registration Form |  |  | 100%
Update
|  |  | HR Profile |  |  | 90%
|  |  | Status |  |  | 80%
Assign
|  |  | Section Teacher |  |  | 100%
|  |  | Subject Teachet |  |  | 100%
Exam Assign
|  |  |  | Class Test |  | 100%
|  |  |  | Semister Exam |  | 100%
|  |  | Account Mapping |  |  | 100%
|  |  | Guide Teacher |  |  | 80%
Report
|  |  | Teacher List |  |  | 100%
|  |  | Assinged Guide Teacher |  |  | 80%
| HR Attendance |  |  |  | 53.33%
Setting
|  |  | Attendance Type |  |  | 100%
Att. Time Setup
|  |  |  | Duty Shift Wise |  | 100%
|  |  |  | HR Wise |  | 100%
|  |  | ID Mapping |  |  | 100%
Take Attendance
|  |  | Daily Attendance |  |  | 60%
Leave Manage
|  |  | Leave Reason |  |  | 0%
|  |  | Leave Input |  |  | 0%
|  |  | Leave Application |  |  | 0%
Delete
|  |  | Attendance |  |  | 0%
|  |  | Leave |  |  | 0%
Report
Summery
|  |  |  | Blank Sheet |  | 60%
|  |  |  | Attendance Preview |  | 60%
|  |  |  | Attendance Status |  | 60%
Details
|  |  |  | Attendance Sheet |  | 60%
|  |  |  | Attendance Info |  | 60%
|  |  |  | Leave Info |  | 0%
Device Report
|  |  |  | Mapping Device |  | 100%
|  |  |  | Device Data Log |  | 100%
Exam Management
| Class Test |  |  |  | 92.5%
Setting
|  |  | Create |  |  | 100%
|  |  | Assign |  |  | 100%
Mark Input
|  |  | Section Wise |  |  | 100%
Mark Update
|  |  | Section Wise |  |  | 100%
Mark Delete
|  |  | Section Wise |  |  | 100%
Report
Mark List
|  |  |  | Section Wise |  | 80%
|  |  |  | Subject Wise |  | 80%
Mark Sheet
|  |  |  | Section Wise |  | 80%
| Semister Exam |  |  |  | 99.2%
Exam Setting
Exam Startup
|  |  |  | Exam Create |  | 100%
|  |  |  | Exam Assign |  | 100%
|  |  |  | Exam Code |  | 100%
|  |  |  | Exam Grade |  | 100%
|  |  |  | Class Test Mapping |  | 100%
|  |  |  | Exam Configure |  | 100%
|  |  |  | Mark Configure |  | 100%
|  |  |  | Exam Date Configure |  | 100%
|  |  |  | Manual Attendance Count |  | 100%
|  |  |  | Grace Mark Config |  | 100%
Mark Input
|  |  | Section Wise |  |  | 100%
Mark Update
|  |  | Section Wise |  |  | 100%
Mark Delete
|  |  | Section Wise |  |  | 100%
Result Process
|  |  | Semister Exam |  |  | 100%
|  |  | Merit Position |  |  | 100%
Reports
Blank Sheet
|  |  |  | Mark Input |  | 100%
|  |  |  | Exam Attendance |  | 100%
Summary
|  |  |  | Unassigned Marks |  | 100%
|  |  |  | Result Info |  | 80%
|  |  |  | Grading Info |  | 100%
|  |  |  | Pass-Fail Info |  | 100%
Details
Exam Result
|  |  |  | Merit List |  | 100%
|  |  |  | Fail List |  | 100%
Exam Layout
|  |  |  | Tabulation Sheet |  | 100%
|  |  |  | Marksheet |  | 100%
Account Management
| Fees Management |  |  |  | 95%
Setting
Fee Startup
|  |  |  | Fee Head |  | 100%
|  |  |  | Fee Sub Head |  | 100%
|  |  |  | Fee Waiver |  | 100%
|  |  |  | Create Sub Group |  | 100%
|  |  |  | Create Ledger |  | 100%
|  |  |  | Create Fund |  | 100%
Fee Mapping
|  |  |  | Fee Mapping |  | 100%
|  |  |  | Fine Mapping |  | 100%
|  |  |  | OPS Mapping |  | 100%
Amount Set
|  |  |  | Classwise Amount |  | 100%
|  |  |  | Studentwise Amount |  | 80%
|  |  |  | Absent Fine Amount |  | 0%
Date Setup
|  |  |  | Assign |  | 100%
|  |  |  | Update |  | 100%
Fee Remove
|  |  |  | Fee Head |  | 100%
|  |  |  | Fee Subhead |  | 100%
Fee Weaver
|  |  |  | Assign |  | 100%
|  |  |  | Assigned List |  | 100%
Fee Collection
Quick Collection
|  |  |  | Section Wise |  | 100%
|  |  |  | Student ID Wise |  | 100%
Delete
|  |  | Paid Invoice |  |  | 70%
Report
Summery
|  |  |  | Payment Ratio |  | 100%
|  |  |  | Head Wise Colection |  | 100%
Details
|  |  |  | Payment Portfolio |  | 100%
|  |  |  | Paid Info |  | 100%
|  |  |  | Due Info |  | 100%
|  |  |  | Weaver Details |  | 100%
|  |  |  | Fee Remove Info |  | 100%
|  |  |  | OPS Collection |  | 100%
|  |  |  | Transaction Log |  | 100%
| General Accounts |  |  |  | 13.16%
Voucher Entry
|  |  | Payment |  |  | 50%
|  |  | Receipt |  |  | 50%
|  |  | Contra |  |  | 50%
|  |  | Journal |  |  | 50%
|  |  | Fund Transfer |  |  | 50%
Voucher Delete
Core Reports
|  |  | Balance Sheet |  |  | 0%
|  |  | Trial Balance |  |  | 0%
|  |  | Income Statement |  |  | 0%
|  |  | Cash Summary |  |  | 0%
|  |  | Cash Flow Statement |  |  | 0%
|  |  | Book of Accounts |  |  | 0%
|  |  | Chart of Accounts |  |  | 0%
Transaction Reports
|  |  | Voucher Wise |  |  | 0%
|  |  | User Wise |  |  | 0%
|  |  | Ledger Wise |  |  | 0%
|  |  | Account Journal |  |  | 0%
|  |  | Fund Wise |  |  | 0%
|  |  | Fund Tran. Summary |  |  | 0%
|  |  | Fund Tran. Monthly |  |  | 0%
Routine Management
| Routine Management |  |  |  | 0%
|  | Create Routine |  |  |  | 0%
|  |  | Class Routine |  |  | 0%
|  |  | Exam Routine |  |  | 0%
|  | Report |  |  |  | 0%
|  |  | Class Routine |  |  | 0%
|  |  |  | Section Wise |  | 0%
|  |  |  | HR Wise |  | 0%
|  |  | Exam Routine |  |  | 0%
|  |  |  | Class Wise |  | 0%
|  |  |  | Exam Wise |  | 0%
Layout Management |  |  |  |  | 33.33%
Layout & Certificate
Template Config
|  |  | Student ID Card |  |  | 0%
|  |  | HR ID Card |  |  | 0%
|  |  | Admit Card |  |  | 100%
|  |  | Seat Card |  |  | 100%
|  |  | Transfer Certificate |  |  | 0%
|  |  | Testimonial |  |  | 0%
|  |  | Dynamic Certificate |  |  | 0%
|  |  | Marksheet |  |  | 100%
Admit Card instruction
Generate Template
|  |  | Student ID Card |  |  | 0%
|  |  | HR ID Card |  |  | 0%
|  |  | Admit Card |  |  | 100%
|  |  | Seat Card |  |  | 100%
|  |  | Transfer Certificate |  |  | 0%
|  |  | Testimonial |  |  | 0%
|  |  | Dynamic Certificate |  |  | 0%
Massege & Notification
| Massage |  |  |  | 73%
Create
Create Template
|  |  |  | General Template |  | 100%
|  |  |  | Notification Template |  | 100%
Phone Book
Send SMS
|  |  | Person Wise | Single SMS |  | 100%
|  |  |  | Students/Parents |  | 80%
|  |  |  | Teacher/Staff |  | 80%
|  |  |  | Excel SMS |  | 100%
|  |  |  | Phone Book SMS |  | 100%
Notification Wise
|  |  |  | Admission SMS |  | 100%
|  |  |  | Birthday SMS |  | 100%
|  |  |  | Attendance SMS |  | 100%
|  |  |  | Date to Date Attendance |  | 100%
|  |  |  | Exam Result SMS |  | 100%
|  |  |  | Class Test SMS |  | 100%
|  |  |  | Due Fee SMS |  | 100%
|  |  |  | Payment SMS |  | 100%
Report
Summery
|  |  |  | Send SMS |  | 0%
Details
|  |  |  | Students/Parents |  | 0%
|  |  |  | Teacher/Staff |  | 0%
|  |  |  | Excel |  | 0%
|  |  |  | Phonbook |  | 0%
Maintanence |  |  |  |  | 100%
Master Setting
Institute Setup
|  |  | Basic Setup |  |  | 100%
|  |  | Startup |  |  | 100%
|  |  |  | Academic Year |  | 100%
|  |  |  | Academic Session |  | 100%
|  |  |  | Shift |  | 100%
|  |  |  | Class |  | 100%
|  |  |  | Section |  | 100%
|  |  |  | Group |  | 100%
|  |  |  | Student Category |  | 100%
|  |  |  | Period |  | 100%
Class Setup
|  |  | Department & Class Mapping |  |  | 100%
Subject Setup
|  |  | Combine Subject Create |  |  | 100%
|  |  | Subject Create |  |  | 100%
|  |  | 4th Subject Assign |  |  | 100%
|  |  | Irregular Subject Assign |  |  | 100%
|  | General Configuration |  |  |  | 100%
Administration |  |  |  |  | 50%
User Management
Role & Permission
|  |  | Create Role |  |  | 100%
|  |  | Set Permission |  |  | 100%
|  | Create User |  |  |  | 100%
|  | Update User |  |  |  | 0%
|  | Reset Password |  |  |  | 0%
|  | User Activity Log |  |  |  | 0%
Auto Enroll
| Online Admission |  |  |  | 100%
Setting
|  |  | Link Manage |  |  | 100%
|  |  | Admission Instruction |  |  | 100%
|  |  | Application Config |  |  | 100%
|  |  | Subject Mapping |  |  | 100%
|  |  | Admission Config |  |  | 100%
|  |  | Enlistment |  |  | 100%
Process
|  |  | Admit Student |  |  | 100%
Report
Applicant
|  |  |  | Applicant Info |  | 100%
|  |  |  | Admission Register |  | 100%
Payment Info
|  |  |  | Collection Info |  | 100%
|  |  |  | Collection Analytics |  | 100%
Online Exam
Live Class Rooms
Homework
Library Management
Hostel Management
Transport Management
Behaviour Records
data comes from software for frontend
HR list
staff list
teacher list
student list
routine info ->
semester exam
fail list
section wise

## Requrement
Label | Module / menu | Sub Module / Sub Menu | Feature | Sub Feature | Requirement | Notes
Student Management | Student Info | Update | Status |  | When a student's toggle status changes the date and time of the toggle action should also be visible here
Administration | User Management | User Activity Log |  |  | The admin portal should allow viewing which user performed which action in the system along with the date and time. | User Activity Log submodule is currently undergoing processing and modifications.
Maintanance | Master Setting | Subject setup | Configure |  | In the combined subject section there should be an automatic subject combination system instead of a manual process as manual handling may cause errors
Student Management | Student Info | Report | Details | Student list | The year in which the student was admitted to the institute should be visible in the student details.
In the dashboard the text "RK EIMS" at the top needs to be changed to "RK EMS"
Administration | User Management |  | Create User |  | Here in the user list the phone number is placed in the username column

## Training Progress (hidden)
https://rkeims.academybd.net/ |  |  |  | https://app.edufee.online/
| Modules | Menus | Training Status | Visibility
1 | Student Module : | Student Info | Completed | Student Info
|  | Student attendance |  | Missing
2 | HR Management : | Human Resource | Completed | Missing
HR Attendance
3 | Exam Module : | Class Test | Completed | Class Test
|  | Semester Exam | Completed | Semester Exam
|  | Combined Result |  | Missing
4 | Account Management : | Fees Management | Completed | Fees Management
|  | General Account | Not Started | Missing
|  | Payroll | Not Started | Missing
|  | Inventory | Not Started | Missing
5 | Routine Management : | Routine | Completed | Missing
6 | Layout Management : | Layout & Certificate | Not Started | Missing
7 | Message & Notification : | Message | Completed | Missing
8 | Maintenance : | Master Settings | Completed | Master Settings
9 | Administration : | User Management | Completed | User Management
10 | Auto Enroll : | Online Admission | Completed | Online Admission
11 | Help Mate : | Support Portal | Completed | Support Portal

## Page issue (hidden)
Pages with issues
Module | Menus | Issues | Resolved Status | Note
Maintenance | Basic Setup | Logo, District, Thana | Solved
| Subject Configure | Clicking Copy to Selected Groups does not copy | Solved
Student Management | Enrollment Form | Manual Entry | Solved | I provided guardian contact number but it is not showing
| Academic Info |  | Solved
| Other Info | All student Excel export ,Student Marital status | Pending
| Day Wise | Time not save | Solved
HR Management | HR Profile | Action | Solved
| Update | Can not Update HR Profile | Pending | Whenever I upload a picture the page refreshes automatically and the entered values are lost.
| Time Setup | Shift Wise , HR Wise | Solved
Exam Management | Class Test | Mark Entry | Solved
| Class Test | Report (All Pages) | Solved
| Semester Exam | Mark Config Update (CT Mapped) | Solved
Account Management | Fee Waiver | Waiver does not update | Pending | I have checked it and it is working correctly. Kindly add a video while checking
| Quick Collection | Fine Date, Expire Date, Fine Amount | Pending
| Collection Invoices |  | solved
| Fees Portfolio | In PDF Paid amount does not show | Solved
| Online Payment Details | Transaction details (after giving date range nothing show) | Solved
| Delete | Fee Collection (Most value dose not show) | Pending
Administration | Create User | Dashboard View | Pending
Auto Enroll | Link Manage | (How to apply & pay)Instruction cannot be set from back office | Pending
| Admission Config | Enable exam date: admit card 404 error | Pending
| Admit Student | Student cannot be admitted | Pending
Student Payment Portal | Available payment | Fine,Waiver not show | solved | can not login payment portal

## httpsems.rksoftbd.com issue (hidden)
Module | Menu | Issue | Status
Back Office
Roles & Permission | Create Role | Role cannot be created.
Institutes | Instruction | Instruction cannot be added.
Institute Portal
Master Settings | Configure | When I copy subjects, the subject group does not copy correctly. | Pending